Renewable Energy Orchestrator (REO)

Implementation, Validation and Commercialisation Plan

Client-ready specification

| Version | 1.1 |
| --- | --- |
| Date | 23 September 2026 |
| Deployment | Cloud-neutral; first client on AWS |
| Market | European electricity market; GDPR applicable |
| Classification | Confidential — client proposal |

# 1. Workstreams

| Workstream | Deliverables |
| --- | --- |
| Product and domain | Country/client market rules, objective policy, operating procedures and KPI baseline. |
| OT integration and safety | Site survey, interface control documents, hazard analysis, command envelopes, HIL/SAT and safety case. |
| Data and digital twin | Source inventory, contracts, quality rules, asset hierarchy, topology and historical replay. |
| Optimisation and AI | Forecasts, scenarios, solver models, agent prompts/guardrails and validation evidence. |
| Platform and security | Cloud/edge infrastructure, IAM, networking, observability, CI/CD, NIS2/IEC 62443 controls. |
| Privacy and governance | DPIA, records, retention, PII controls, AI risk classification and human oversight. |
| Change and operations | Training, SOPs, incident response, support model and autonomy progression. |
| Commercial productisation | Tenant packaging, configuration catalogue, licences, pricing meter and reusable evidence. |

# 2. Indicative phased plan

| Phase | Indicative duration | Exit criteria |
| --- | --- | --- |
| 0 Discovery & assurance | 4–6 weeks | Market/site scope, data access, DPIA draft, hazards, KPIs and architecture agreed. |
| 1 Data/twin foundation | 8–12 weeks | Historical/live ingestion, asset model, data quality and replay operational. |
| 2 Forecast/simulation/optimisation | 10–14 weeks | Back-tested models and feasible plans across named scenarios. |
| 3 Observe & recommend pilot | 6–8 weeks | Shadow operation meets latency, quality and value thresholds. |
| 4 Approval-controlled production | 8–12 weeks | HIL/FAT/SAT complete; approved actions executed safely. |
| 5 Bounded autonomy | Client risk-led | Specific action classes enabled after evidence and governance approval. |
| 6 Scale/productise | Ongoing | 2× scale, automated onboarding, portability and service operations. |

# 3. Acceptance gates

| Gate | Evidence |
| --- | --- |
| G1 Data readiness | Coverage, quality, units, clocks, lineage and PII controls. |
| G2 Model readiness | Baseline comparison, uncertainty calibration, drift and fallback. |
| G3 Optimisation readiness | Feasibility, objective traceability, scenario performance and independent validation. |
| G4 Security/privacy | Pen test, threat model, DPIA, access review, SBOM and incident exercises. |
| G5 OT safety | Hazard analysis, command envelope, HIL/FAT/SAT, emergency stop and local fallback. |
| G6 Operational readiness | SLOs, monitoring, runbooks, training, on-call and DR restore. |
| G7 Autonomy approval | Action-specific safety case, demonstrated shadow performance and named accountable owner. |

# 4. Demonstration script

Start with normal solar/wind/demand; show live portfolio and 24-hour plan.

Apply cloud cover; show solar forecast reduction, battery response and plan explanation.

Apply wind surge and price spike; show charge/sell trade-off and market-period mapping.

Make one battery unavailable; demonstrate constraint update and re-optimisation.

Constrain a transmission line; show curtailed/shifted actions and reliability priority.

Increase industrial demand unexpectedly; show demand response and reserve use.

Switch modes from Observe to Recommend to Approval; approve one action and reject another.

Enable a narrow autonomous policy; execute a low-risk action through prepare/commit/acknowledge.

Inject stale telemetry and a malicious document instruction; demonstrate autonomy downgrade and guardrail alert.

Export the complete decision evidence and KPI impact.

# 5. Commercial packaging

| Edition | Positioning |
| --- | --- |
| Insight | Ingestion, digital twin, forecasts, dashboards and Observe mode. |
| Optimise | Scenario lab, optimisation, recommendations and value analytics. |
| Control | Approval-controlled OT execution, safety gateway and 24×7 operations. |
| Autonomous | Policy-bounded autonomy for certified action classes with enhanced assurance. |
| Accelerator | Single-client isolated deployment using the same product core and IaC. |

# 6. Client prerequisites

Named executive, operational, OT safety, cybersecurity, DPO and market owners.

Approved access to telemetry, asset limits, topology, forecasts, market/contract data and historical outcomes.

SCADA/EMS vendor engagement and test environment/simulator.

Country-specific legal, grid-code, market and AI classification review.

Baseline operating procedure and KPI calculation agreement.

Change-management commitment: operators participate in design, drills and autonomy gates.

# 7. Principal risks and mitigations

| Risk | Mitigation |
| --- | --- |
| Poor/stale data | Quality contracts, state confidence, fallback and autonomy downgrade. |
| Forecast error/tail event | Probabilistic scenarios, CVaR, reserves, event re-plan and operator escalation. |
| Unsafe optimisation defect | Independent validator, property tests, HIL and action envelope. |
| Agent hallucination/injection | Typed tools, evidence grounding, no direct control and adversarial evaluation. |
| OT connectivity failure | Edge buffering, local safe policy and SCADA authority. |
| Market-rule mismatch | Country configuration pack and legal/market acceptance gate. |
| Cross-tenant leakage | Tenant-scoped identity, storage, retrieval and automated isolation tests. |
| Operator distrust | Transparent explanations, replay, shadow mode and progressive autonomy. |
| Regulatory change | Policy/version service and maintained compliance roadmap. |
| Vendor lock-in | Open interfaces, containers, infrastructure-as-code and solver/model adapters. |

# Reference sources

| Source | Use in specification |
| --- | --- |
| EU Electricity Regulation (EU) 2019/943 | Reference imbalance settlement period is 15 minutes, subject to applicable exemptions. |
| Commission Regulation (EU) 2017/2195 | Electricity balancing and imbalance-settlement framework. |
| GDPR Regulation (EU) 2016/679 | Data protection by design/default, data minimisation and DPIA obligations. |
| NIS2 Directive (EU) 2022/2555 | Cybersecurity risk management applicable to relevant energy entities. |
| EU AI Act / European Commission guidance | Potential high-risk treatment where AI is a safety component in critical infrastructure; classification must be assessed for the deployed use case. |
| IEC 62443 series | Industrial automation and control-system cybersecurity principles. |
| AWS IoT SiteWise and AWS IoT Greengrass official documentation | AWS-specific industrial-edge and OPC UA implementation reference. |

# 8. Platform delivery, validation and commercialisation additions

Add a Platform Foundation workstream covering tenant control plane, Decision Centre, Approval Inbox, Connector Studio, Export Service, credential broker, subscription/entitlement hooks and platform operations. Delivery shall preserve the option of a shared multi-tenant SaaS deployment or a dedicated single-tenant accelerator deployment.

The pilot demonstration shall include: a market price spike causing an energy procurement/sale decision; a renewable forecast change causing source rebalancing; a BESS availability event; an approval-gated SCADA/BESS signal; human connector configuration and test; approval and execution; external acknowledgement; live dashboard lineage; and Excel export of decisions, reasoning, approvals and signals.

Production go-live requires penetration testing of connector configuration and outbound request controls, OT safety and fail-safe tests, approval concurrency and stale-decision tests, tenant-isolation tests, export leakage/formula-injection tests, credential-rotation tests, API contract tests, disaster recovery exercise and operator training.

| Gate | Evidence required |
| --- | --- |
| Platform readiness | Tenant provisioning, role separation, configuration versioning, health monitoring and support runbooks. |
| Decision transparency | 100% of material decisions and signal lifecycle states visible and traceable in dashboard. |
| Connector security | Endpoint validation, egress restriction, vault integration, dry run, maker-checker activation and emergency disable proven. |
| Human governance | Approve/reject/modify/expire/re-plan workflows tested including stale and conflicting approvals. |
| OT execution safety | Final deterministic checks, interlocks, idempotency, acknowledgement, timeout and rollback tested with simulator and site interface. |
| Excel export | Required sheets/fields, filters, redaction, formula-injection protection, checksum, expiry and download audit verified. |
| Multi-tenancy | Cross-tenant access tests pass for API, dashboard, events, storage, exports, logs and support access. |
| Commercial packaging | Shared-platform and dedicated-deployment SKUs, service boundaries, SLA, implementation package and licensing assumptions documented. |

Version 1.1 update scope: Platform product positioning; complete decision/signal dashboard lineage; governed Excel export; human-configurable API integration and authentication; approval-gated execution; and strengthened multi-tenant, OT and connector security controls.